## 22.01.2019
"Approved" Chief Engineer JSC Ukrtransgaz ____________________ " ____ " _________________ 2019
JSC Ukrtransgaz' schedule of maintenance and repair works that influence Russian gas transit in 2019
| List of fire works | Term, hours | Gas volume to be intaken/supplied at GMS | Note
Complex No. 1 (14.05 - 16.05)
| Preventive - maintenance works on YeKK - YEKD, ShPK -ShDK-YeDK pipelines at Romny CS, Sumy CS, Hrebinka CS and Yahotyn CS. Valve replacement, Dn 300, Romny CS. Defect elimination on the pipelines. | 72 | Max gas intake at Sudzha GMS (Р=55) Q=24 mln.m3/day. | Gazprom - Blue stream
Complex No.2 (21.05 - 23.05)
| Preventive - maintenance works on UPU: Romny CS (120), Hrebinka CS, Sofiivka CS, Stavyshche CS, Illintsi CS, Husityn CS, Bohorodchany CS and Holiatyn CS. Defect elimination on the pipeline | 72, 120 | Max gas supply through Beregove GMS =40 mln.m3/day, Теkovo=1 mln.m3/day, Drozdovychi=12 mln.m3/day, Oleksiivka =1 mln.m3/day, Uzhgorod =158 mln. m3/day. Gas flow reallocation by directions is possible. If the gas is supplied through Kobryn GMS and Mozyr GMS, it is possible to enhance gas transit up to 40 mln.m3/day through Uzhgorod GMS Max gas intake at Sudzha GMS (Р=75) Q=200 mln.m3/day.
Complex No 3 (28.05 - 30.05)
| Preventive - maintenance works on Progress pipeline: Romny CS (120), Hrebinka CS, Sofiivka CS, Stavyshche CS, Illintsi CS, Husityn CS, Bohorodchany CS and Holiatyn CS. Valve replacement Dn 1000 and Dn 500 at CS -32П. Defect elimination on pipelines. | 72, 120 | Max gas supply through Beregove GMS =40 mln.m3/day, Теkovo=1 mln.m3/day, Drozdovychi=12 mln.m3/day, Oleksiivka =1 mln.m3/day, Uzhgorod =158 mln.m3/day. Gas flow reallocation by directions is possible. If the gas is supplied through Kobryn GMS and Mozyr GMS, it is possible to enhance gas transit up to 40 mln.m3/day through Uzhgorod GMS. Max gas intake at Sudzha GMS (Р=75) Q=200 mln.m3/day. | Gazprom - Tulskyi
Complex No 4 (04.06 - 07.06)
| Preventive - maintenance works on YeKKR, КАB, АТІ pipelines at Romny CS (120), Reshetylivka CS, Kirovohradska CS,Ananiiv CS, Orlovka -2 CS. Valve replacement Dn 700 Romny CS-3. Defect elimination on pipelines and Hrebenyky GMS. | 96, 120 | Max gas intake at Sudzha GMS (Р=75) Q=170 mln.m3/day. Max gas supply through Orlovka GMS Q=45 mln.m3/day, operating pressure reduction up to 0,7 Pa. Tyraspil CS (ShDKRI pipeline) and Vulcanesti CS are in operation | Balkan stand-by June 04-07, 2019
Complex No 5 (11.06 - 13.06)
| Preventive - maintenance works on ShPK- ShDK-YeDK pipelines Lubny CS and КZU-1,2 pipeline and Krasyliv CS (96). Vent valve replacement of junction point Krasyliv CS. Defect elimination on pipelines. | 72, 96 | Max gas supply through Sudzha GMS (Р=55) Q=24 mln. m3/day.
Complex No 6 (19.06 (Wednesday) - 21.06)
| Preventive - maintenance works on ShPK -ShDK-YeDK and KZU-1,2 at Berdychiv CS (120) and Rohatyn CS. Valve replacement No. 1 and No. 2 GPU No. 4 Berdychiv CS. Defect elimination on pipelines. | 72, 120 | Max gas supply through Sudzha GMS (Р=55) Q=24 mln. m3/day.
Complex No 7 (02.07 - 04.07)
| Preventive - maintenance works on Soyuz pipeline: Borova CS, Mashivka CS, Husiatyn CS, Khust CS. Vent valve replacement No. 19 Dn 300 Khust CS. Reverse valve replacement No. 7р Dn 1000 Khust CS ( 2569,3 km - 2573,0 km pipeline switching ). Defect elimination on the pipeline. | 72 | Max gas supply through Beregove GMS =38 mln.m3/day, Теkovo=1 mln.m3/day, Drozdovychi=11 mln.m3/day, Oleksiivka =1 mln.m3/day, Uzhgorod =155 mln.m3/day. Gas flow reallocation by directions is possible. Max gas intake at Sudzha GMS (Р=75) Q=200 mln.m3/day. Suspension of the gas transit through Khust CS of Soyuz pipeline. | Surgutskyi-2 (Urengoi-Novopskov). Possible stopage of Pysarivka 1400
Complex No 8 (31.07 - 02.08)
| Preventive - maintenance works on Soyuz pipeline: Soyuz CS, Pervomaiska CS, Bohorodchany CS. Defect elimination on the pipeline. | 72 | Max gas supply through Beregove GMS =37 mln.m3/day, Теkovo=1 mln.m3/day, Drozdovychi=11 mln.m3/day, Oleksiivka =1 mln.m3/day, Uzhgorod =161 mln.m3/day. Gas flow reallocation by directions is possible. Max gas intake at Sudzha GMS (Р=75) Q=200 mln.m3/day, Pysarivka GMS (Р=75) Q=60 mln.m3/day.
Complex No 9 (06.08 - 08.08)
| Preventive - maintenance works on Komarno-Drozdovychi pipeline Komarno CS and KZU -1,2 pipeline at Boiarka CS.Defect elimination on pipelines. Defect elimination Komarno-State boarder pipeline Dn 700. | 72 | Max gas supply through Drozdovychi GMS Q=10 mln.m3/day. Suspension of the gas supply through Hermanowice GMS.
Complex No 10 (12.08 (Monday) - 15.08)
| Preventive - maintenance works on YeKKR, КАChB and АТІ pipelines Zinkiv CS (120), Zadniprovska CS, P. Buzka CS, Orlovka -1 CS.Defect elimination on pipelines. | 96, 120 | Max gas supply through Orlovka GMS Q=45 mln.m3/day, with operating pressure reductiion up to 0,7Рa. Tyraspil CS (ShDKRI pipeline) and Vulcanesti CS are in operation. Max gas supply through Beregove, Tekove GMSs Uzhgorod Q = 170 mln.m3/day. Max gas supply through Sudzha GMS (Р=75) Q=170 mln.m3/day. | Balkan Main August 12-15, 2019
Complex No 11 (10.09 - 12.09)
| Preventive - maintenance works on YeKK and KZU-1,2 pipelines Hlushkiv CS and ternopil CS. Defect elimination on pipelines. | 72 | Max gas supply through Sudzha GMS (Р=55) Q=24 mln. m3/day.
Complex No 12 (08.10 - 10.10)
| Preventive - maintenance works on ShPK-ShDK-YeDК Dykanka CS. Defect elimination on pipelines. | 72 | Максимальний прийом газу через ГВС Суджа (Р=55) Q=24 млн.м3/доб
Complex No 13 (August -September)
| Preventive - maintenance works on DUD-2 pipeline being performed step-by-step: Dolyna - 2, 3 CS; Rososh CS; Uzhgorod GCS. Defect elimination on pipelines. | 144 | Max gas supply through Beregove GMS =41 mln.m3/day, Теkovo=2 mln.m3/day, Drozdovychi=12 mln.m3/day, Oleksiivka =1 mln.m3/day, Uzhgorod =156 mln.m3/day. Gas flow reallocation by directions is possible.
Repair works on the pipelines: January - December 2019
| Overhaul of UPU main pipeline. Section 322,1 km (exit at Romny CS) - 3370,32 km. Switching 48,2 km. Section 3488,36 km (exit at Hrebinkivska CS) - 3538,1 km. Switching 49,7 km. Section 3974,77 km (exit at Bar CS) - 4008,45 km. Switching 59 km. Section 4101,3 km (exit at Husiatyn CS) - 4128,4 km. Switching 57 km. | March -December | Max gas supply through Beregove GMS =35 mln.m3/day, Теkovo=2 mln.m3/day, Drozdovychi=12,5 mln.m3/day, Oleksiivka =2 mln.m3/day, Uzhgorod =161 mln.m3/day. Gas flow reallocation by directions is possible. Gas flow reallocation by directions is possible. If the gas is supplied through Kobryn GMS and Mozyr GMS, it is possible to enhance gas transit up to 40 mln.m3/day through Uzhgorod GMS Max gas supply through Sudzha GMS (Р=75) Q=200 mln.m3/day.
| Repair of protective coating on the earth trench edge by pipeline replacement and joints reinstallation on Komarno-Drozdovychi pipeline, Dn 500 | 1440
| Repair of protective coating on the earth trench edge by pipeline replacement and joints reinstallation on Ivatsevychi-Komarno pipeline, Dn 800 (looping). Section 55,609 km - 55,361 km | 3 months (June - August)
| Repair of protective coating on the earth trench edge by pipeline replacement and joints inspection on KZU-ІІ pipeline, Dn 1200. Section 523,905 km - 524,705 km | 2 monkths (January -March)
| Replacement of unround valves, Dn 1000 (no. 3Т and no.8) required piping KZU-І pipeline. Section Ternopil CS - K. Buzka CS | 2 weeks
| Defect elimination on Komarno pipeline - State boarder, Dn 700 | 2 weeks
| Repair of protective coating on the earth trench edge by pipeline replacement and joints inspection on Pukenychi - Komarno pipeline, Dn 700. Section 4,32 km- 6,37 km | 2 months
Subsequent repair of protective coating of the main pipeline with pressure reduction not less than 10 % max flow-through pressure: - YeККR 382,9 km - 383,54 km, Sumy MPD; - ShPК 126,454 km - 128,723 km, ShDК 129,006 km - 130,216 km, 213,558 km - 217,925 km, GB to Khrestyshche GP 10,08 km - 11,502 km, Dykanka MPD; - ShDК 288,71 km - 290,589 km, stand-by line ShDK 0,0 km - 1,513 km, YeDК 256,52 km - 257,635 km, Hnidyntsi GB -ShPK 25,146 km - 28,865 km, GB Chornuhy GMS 21,55 km - 22,8 km, Lubny MPD; - YeКК 387,434 km - 389,11 km, ShPK 404,217 km - 405,271 km, Yahotyn MPD; - KZU-ІІ pipeleine 22,228 km - 25,948 km, ShDK 494,567 km - 496,651 km, Boiarka MPD; - steel casing pipe reinstallation 431,152 km, ShDK pipeline, Yahotyn MPD.
Replacement of defective valves on gas branches to GMS's of Dykanka, Sumy, Boiarka and Krasyliv MPD.
Switching of ShDK pipeline 245,67 km - 252,566 km, Lubny MPD with the aim to perform subsequent protective coating.
Defect elimination by steel reinforcing coupling with operating flow-through pressure of 0,7 Pa on the YeKKR, YeKD, ShDK-YeDK-ShPK, KZU -1, 2 pipeline
| Defect elimination on DUD-ІІ pipeline 7,25 km - 58,86 km with pressure reduction up to 38,5 kgf/cm2 | 240
| Defect elimination on Soyuz pipeline 2317 km - 2426 km (Husiatyn CS - Bohorodchany CS) with the pressure reduction upto 52,5 kgf/cm2 | 96
| Defect elimination on Soyuz pipeline, section 2428 km - 2496 km (Bohorodchany CS - Khust CS) with the pressure reduction upto 52,5 kgf/cm2 | 48
| Defect elimination on Soyuz pipeline, section 2504,9 km - 2562,24 km (Bohorodchany CS - Khust CS) with the pressure reduction upto 52,5 kgf/cm2 | 72
| Defect elimination on Soyuz pipeline, section pipelines 2596,5 km - 2670,53 km, Khust CS - Uzhorod CS with the pressure reduction upto 52,5 kgf/cm2 | 168
| Defect elimination on UPU pipeline, 4109 km - 4237 km (Husiatyn CS - Bohorodchany CS) with the pressure reduction upto 52,5 kgf/cm2 | 144
| Defect elimination on UPU pipeline, 4239 km- 4282 km (Bohorodchany CS - Holiatyn CS) with the pressure reduction upto 52,5 kgf/cm2 | 48
| Defect elimination on UPU pipeline, section 4294,09 km (Bohorodchany CS - Holiatyn CS ) with the pressure reduction upto 52,5 kgf/cm2 | 24
| Defect elimination on KAChB pipeline, section 622,4 km - 699 km (State boarder - Khust CS) with the pressure reduction upto 38,5 kgf/cm2 | 240
| Defect elimination on KAChB pipeline, section 699 km- 879,5 km (Khotyn CS - Bohorodchany CS) with the pressure reduction upto 38,5 kgf/cm2 | 240
| Overhaul of RI pipeline,Dn 800 section 283 km - 286 km, with the partial replacement of the protective coating | 2184
| Overhaul of ShDO-1 pipeline,Dn 500, section 277,645 km - 283,2 km, with partial replacement of the protective coating | 2340
| Valves' replacement (valve no. 19) on section 96,25 km, Odesa - Kyshyniv pipeline caused by sealing . | 168
| Defect elimination on ATI pipeline, section 29 km - 328,7 km with the pressure reductiion upto 52,5 kgf/cm2 | 240
| DUD-ІІ. (176,25 km). Overhaul of the GMSP joint of Uzhgorod GMS, with switching DUD - II, 1,78 km | 120 | Suspension of Budince GMS
Preventive - maintenance works on Soyuz pipeline at Kremenchuk, Oleksandrivka, Talne, Haisyn CSs and Bar CS (UPU, Progress, Soyuz pipelines) are suggested to perform before Complex No. 2 (until 21.05.2019). Should it is not possible to perform such works before 21.05.19, permissions to provide these works will be issued depending on the GTS operation mode.
Taking into account expiration date of high perssure vessel use and necessity to provide license inspection and hydraulic pressure tests of the vessels at Zinkiv CS Reshetylivka CS it is suggested to perform the above mentioned works before preventive maintenance repairs at the mentioned CSs.
Approved:
| Central dispatching department of TSO Branch |  | Gas metering devision
| Frolov A.V. |  | Bolhovitin М.І.
Gas transportation department
Samchenko І.А.